## Page Inventory
aiDataWorks Website — Page Inventory
Rows 1-30: every HTML page that exists in the repo today, re-verified against index.html's actual nav/footer source. Rows 31-40: pages/content not built yet but called for (see Status + Notes). Generated 2026-08-11, updated 2026-08-12.
# | Category | Page Name | File Path | Page Title | Status | In Top Nav? | In Footer? | Also Linked From (other pages) | styles.css? | site.js? | Notes
1 | Landing Page | Homepage | index.html | aiDataWorks | Live | N/A | N/A | Site root | Yes | Yes | 2x logo (.nav-logo--lg / .footer-logo--lg) scoped to this page only.
2 | Overview | Services Overview | services.html | Services ¦ aiDataWorks | Live | Yes — Services dropdown (promo link + "View all Services" foot link) | No |  | Yes | Yes | One-pager built from all 6 Services dropdown tabs. Anchors: advisory-assessment, implementation-delivery, managed-dmaas, licensing-reselling, training-enablement, staff-augmentation. NOTE: the footer's "Services" column heading is plain text, not a link to this page — verified in the raw footer markup.
3 | Overview | Solutions Overview | solutions.html | Solutions ¦ aiDataWorks | Live | Yes — Solutions dropdown (promo link + "View all Solutions" foot link) | No |  | Yes | Yes | One-pager built from all 10 Solutions dropdown tabs. Anchors: legacy-modernization, cloud-data-platforms, data-integration, mdm, governance-quality-catalog, analytics-insights, b2b-data-exchange, data-security-privacy, dataops-observability, ai-agentic-solutions. NOTE: the footer's "Solutions" column heading is plain text, not a link — same as Services.
4 | Industry | Healthcare Industry Page | industry-healthcare.html | Healthcare ¦ aiDataWorks | Live | Yes — Industries dropdown | Yes — Industries column |  | Yes | Yes | Has a Related Case Studies section (populated).
5 | Industry | Financial Services Industry Page | industry-financial-services.html | Financial Services ¦ aiDataWorks | Live | Yes — Industries dropdown | Yes — Industries column |  | Yes | Yes | Has a Related Case Studies section (populated).
6 | Industry | Insurance Industry Page | industry-insurance.html | Insurance ¦ aiDataWorks | Live | Yes — Industries dropdown | Yes — Industries column |  | Yes | Yes | Has a Related Case Studies section (populated).
7 | Industry | Manufacturing Industry Page | industry-manufacturing.html | Manufacturing ¦ aiDataWorks | Live | Yes — Industries dropdown | Yes — Industries column |  | Yes | Yes | Has a Related Case Studies section (populated).
8 | Industry | Retail & CPG Industry Page | industry-retail-cpg.html | Retail & CPG ¦ aiDataWorks | Live | Yes — Industries dropdown | Yes — Industries column |  | Yes | Yes | Has a Related Case Studies section (populated).
9 | Industry | Public Sector Industry Page | industry-public-sector.html | Public Sector ¦ aiDataWorks | Live | Yes — Industries dropdown | Yes — Industries column |  | Yes | Yes | Related Case Studies section shows the empty state — no Public Sector case study exists yet.
10 | Company | About Us | about.html | About Us ¦ aiDataWorks | Live | Yes — About dropdown (Who We Are) + promo link | Yes — About column |  | Yes | Yes
11 | Company | Careers | careers.html | Careers ¦ aiDataWorks | Live | Yes — About dropdown | Yes — About column |  | Yes | Yes
12 | Company | Contact Us | contact.html | Contact Us ¦ aiDataWorks | Live | Yes — About dropdown + "Talk to an Expert" CTA button | Yes — About column |  | Yes | Yes | Contact info updated this cycle: sam.singh@aidata.works / +1 630 346-1120 / calendly.com/sam-singh-aidata/30min.
13 | Resources | Case Studies Index | case-studies.html | Case Studies ¦ aiDataWorks | Live | Yes — Resources dropdown | Yes — Resources column | Homepage hero secondary CTA ("Explore Case Studies") | Yes | Yes | Grid is rendered client-side from a JSON data block — all 13 case studies present. Old resource-tab row (Blogs ¦ Case Studies ¦ FAQs ¦ Events ¦ Whitepapers ¦ Newsroom) removed per request.
14 | Resources | Webinars & Events | webinars.html | Webinars & Events ¦ aiDataWorks | Live | Yes — Resources dropdown ('Events') | Yes — Resources column |  | Yes | Yes
15 | Legal | Privacy Policy | privacy.html | Privacy Policy ¦ aiDataWorks | Live | No | Yes — legal row |  | Yes | Yes | Standard footer-legal-only placement, not in top nav — same pattern as Terms.
16 | Legal | Terms of Service | terms.html | Terms of Service ¦ aiDataWorks | Live | No | Yes — legal row |  | Yes | Yes | Standard footer-legal-only placement, not in top nav — same pattern as Privacy.
17 | Case Study | Case Study: Microfinance Platform Modernization | case-studies/bfsi-microfinance-platform-modernization/index.html | Microfinance Data Platform Modernization ¦ aiDataWorks Case Study | Live | No | No | case-studies.html grid (in top nav + footer); related-case-study cards | Yes | Yes
18 | Case Study | Case Study: Regional Bank B2B Modernization | case-studies/frost-bank-b2b-nacha-edi-modernization/index.html | Building an In-House NACHA-to-EDI 820 Exchange for a Tier 1 Regional Bank — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-financial-services.html | Yes | No | BUG: missing <script src="../../site.js"> — mobile menu accordion won't work on this page. Client name anonymized this cycle (was named).
19 | Case Study | Case Study: Cleo to Informatica MFT Migration | case-studies/life-sciences-mft-migration/index.html | Cleo to Informatica MFT Migration — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards | Yes | No | BUG: missing site.js script tag.
20 | Case Study | Case Study: AI Data Quality & Governance on IDMC | case-studies/ai-data-quality-governance-idmc/index.html | Automating Data Quality, Governance & Predictive Insights on IDMC — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards | Yes | No | BUG: missing site.js script tag.
21 | Case Study | Case Study: AI Interoperability & Predictive Patient Care | case-studies/healthcare-ai-interoperability-patient-care/index.html | AI-Powered Interoperability and Predictive Patient Care on IDMC — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-healthcare.html | Yes | Yes
22 | Case Study | Case Study: Healthcare Credentials Modernization | case-studies/corewell-health-credentials-modernization/index.html | Modernizing Application Credentials for a Tier 1 Healthcare System — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-healthcare.html | Yes | No | BUG: missing site.js script tag. Client name anonymized this cycle (was named Corewell Health).
23 | Case Study | Case Study: Retail Big Data Engineering & Cloud Migration | case-studies/retail-bde-cloud-migration/index.html | Unblocking a Retailer's Big Data Engineering Upgrade & Cloud Cost — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-retail-cpg.html | Yes | No | BUG: missing site.js script tag.
24 | Case Study | Case Study: Sensitive Patient Data Protection | case-studies/healthcare-sensitive-data-protection/index.html | Identifying, Masking and Democratizing Sensitive Patient Data — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-healthcare.html | Yes | No | BUG: missing site.js script tag.
25 | Case Study | Case Study: Health Insurer Mainframe Governance | case-studies/health-insurer-mainframe-governance/index.html | Governing Legacy Mainframe COBOL Data for a Health Insurer — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-insurance.html | Yes | No | BUG: missing site.js script tag.
26 | Case Study | Case Study: Healthcare Post-Go-Live Managed Services | case-studies/healthcare-managed-services-post-golive/index.html | Post-Go-Live Managed Services for a Healthcare Informatica Estate — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-healthcare.html | Yes | No | BUG: missing site.js script tag.
27 | Case Study | Case Study: Semiconductor Industry 4.0 Analytics | case-studies/semiconductor-industry40-analytics-transition/index.html | Industry 4.0 and OEE Analytics Transition for a Semiconductor Manufacturer — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-manufacturing.html | Yes | No | BUG: missing site.js script tag.
28 | Case Study | Case Study: Semiconductor Data Security & Cloud Warehouse | case-studies/semiconductor-data-security-cloud-warehouse/index.html | Securing Shop-Floor Data in the Cloud for a Semiconductor Manufacturer — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-manufacturing.html | Yes | No | BUG: missing site.js script tag.
29 | Case Study | Case Study: Healthcare HL7 Real-Time Integration | case-studies/healthcare-hl7-realtime-integration/index.html | Near-Real-Time HL7 Integration for a Cloud Help Desk Platform — Case Study ¦ aiDataWorks | Live | No | No | case-studies.html grid; related-case-study cards; industry-healthcare.html | Yes | No | BUG: missing site.js script tag.
30 | Template | Case Study Build Template | templates/case-study-template.html | Real-Time Customer Onboarding in BFSI — Case Study ¦ AI Dataworks | Dev-only (moved out of public path) | No | No | Not linked from any page (intentional) | Yes | No | Moved this cycle from case-studies/case-study-template.html to templates/case-study-template.html so it no longer sits alongside real, published case studies. Relative links (../styles.css etc.) still resolve correctly since templates/ is the same folder depth as case-studies/. Kept in the repo for building future case-study pages, per request. Note: it's still statically reachable if someone knows the URL, since GitHub Pages serves the whole repo — add a noindex meta tag or robots.txt rule if that matters.
31 | Missing / Planned | Partners Overview (proposed: partners.html) | — not built yet | — | Missing (High Priority) | Yes — but all 15 links alias to #partners anchor, not a real page | No |  | N/A | N/A | All 15 alliance/platform links in the Partners nav dropdown point to the same generic homepage logo-wall anchor. CAN BUILD NOW — no new content needed, partner names + 2 category groupings already exist in the nav dropdown itself. Follow the same one-pager pattern as services.html/solutions.html.
32 | Missing / Planned | Blog (proposed) | — not built yet | — | Missing (High Priority) | Yes — aliases to #insights anchor (shows case studies, not blog content) | No |  | N/A | N/A | The "Blogs" nav item points to the homepage #insights anchor, which shows 4 case-study teasers, not blog content. CANNOT build yet — needs real blog post content from you first.
33 | Missing / Planned | Whitepapers (proposed) | — not built yet | — | Missing (High Priority) | Yes — aliases to same #insights anchor as Blogs | No |  | N/A | N/A | Same anchor as Blogs — shows case studies, not whitepapers. No resource library exists. CANNOT build yet — needs whitepaper assets (PDFs) and descriptions from you first.
34 | Missing / Planned | Newsroom / Press (proposed) | — not built yet | — | Missing (High Priority) | Yes — aliases to same #insights anchor as Blogs | No |  | N/A | N/A | Same anchor as Blogs — shows case studies, not press/news. No newsroom page exists. CANNOT build yet — needs press releases/media mentions/press contact info from you first.
35 | Missing / Planned | Leadership / Team (proposed) | — not built yet | — | Missing (Medium-High Priority) | No | No |  | N/A | N/A | about.html has a "Who We Are" narrative but zero people — no founder/leadership names, titles, bios, or photos. Credibility gap for a professional-services firm. CANNOT build yet — needs names/titles/bios/headshots from you. Could be a new section on about.html or its own page.
36 | Missing / Planned | Trust / Security & Compliance (proposed) | — not built yet | — | Missing (Medium-High Priority) | No | No |  | N/A | N/A | Clients are in regulated industries (healthcare/HIPAA, BFSI). Compliance messaging is scattered across an FAQ answer, the Governance section, and one dropdown blurb, with no single reviewable page. CANNOT build yet — needs real security/compliance practices, certifications, and data handling policy from you. Common ask during enterprise security review before a first sales call in these industries.
37 | Missing / Planned | 404 error page (proposed) | — not built yet | — | Missing (Medium Priority) | N/A | N/A |  | N/A | N/A | Doesn't exist — a broken/mistyped link currently falls through to a raw server error instead of a branded page with a way back into the site. CAN BUILD NOW — no new content needed, just page chrome + a link home.
38 | Missing / Planned | robots.txt / sitemap.xml (proposed) | — not built yet | — | Missing (Medium Priority) | N/A | N/A |  | N/A | N/A | Neither exists — search engines have no crawl guidance and no full list of the site's pages to index. CAN BUILD NOW — no new content needed; sitemap.xml can be generated directly from this sheet's 31 live pages (rows 1-31).
39 | Missing / Planned | Services: distinct content per sub-offering (proposed) | — not built yet | — | Missing (Medium Priority) | Partial fix shipped | N/A |  | N/A | N/A | Team feedback (2026-08-12): the Services nav dropdown lists 27 individually-named offerings across 6 categories (e.g. "AI Readiness Assessment", "Data Governance Maturity Assessment" under Advisory & Assessment) but all of them link to the same one category-level anchor on services.html — nothing distinguishes them once you land on the page. CHEAP FIX ALREADY SHIPPED: the 6 category labels themselves are now clickable links (previously just JS tab-switcher buttons with no href), so hovering-then-clicking a category no longer dead-ends. THIS ROW is the deeper, still-open fix: give each of the 27 named offerings its own real anchor/content within services.html, or — if several of them genuinely are just facets of one offering — stop presenting them as separately-clickable rows in the dropdown. Needs a content/IA decision, not just code.
40 | Missing / Planned | Solutions: distinct content per sub-offering (proposed) | — not built yet | — | Missing (Medium Priority) | Partial fix shipped | N/A |  | N/A | N/A | Team feedback (2026-08-12): same pattern as Services, larger scale — the Solutions nav dropdown lists 40 individually-named offerings across 10 categories, all funneling to just 10 category-level anchors on solutions.html. CHEAP FIX ALREADY SHIPPED: the 10 category labels are now clickable links. THIS ROW is the deeper fix: give each of the 40 named offerings real distinct content, or simplify the dropdown so it stops implying 40 separate destinations. Same content/IA decision needed as the Services row above.

## Nav & Footer Link Map
Nav / Footer Link Targets
Where every top-nav and footer link currently resolves, and any dead or aliased links found in the current code.
# | Location | Link Label | Target | Resolves To | Status | Notes
1 | Nav → Services dropdown | Advisory & Assessment (5 links) | services.html#advisory-assessment | services.html, Advisory & Assessment section | Live | FIXED 2026-08-12: the category label itself (e.g. "Advisory & Assessment") is now a real link too, not just its 5 sub-items — same for all 6 Services categories. The 5 sub-items still all resolve to this one anchor; see Page Inventory row 39 for that still-open item.
2 | Nav → Services dropdown | Implementation & Delivery (6 links) | services.html#implementation-delivery | services.html, Implementation & Delivery section | Live
3 | Nav → Services dropdown | Managed Services — DMaaS (4 links) | services.html#managed-dmaas | services.html, Managed DMaaS section | Live
4 | Nav → Services dropdown | Licensing & Reselling (4 links) | services.html#licensing-reselling | services.html, Licensing & Reselling section | Live
5 | Nav → Services dropdown | Training & Enablement (4 links) | services.html#training-enablement | services.html, Training & Enablement section | Live
6 | Nav → Services dropdown | Staff Augmentation (4 links) | services.html#staff-augmentation | services.html, Staff Augmentation section | Live
7 | Nav → Solutions dropdown | Legacy Modernization & Cloud Migration | solutions.html#legacy-modernization | solutions.html section | Live | FIXED 2026-08-12: the category label itself is now a real link too, not just its sub-items — same for all 10 Solutions categories. Sub-items still all resolve to one anchor per category; see Page Inventory row 40 for that still-open item.
8 | Nav → Solutions dropdown | Cloud Data Platforms | solutions.html#cloud-data-platforms | solutions.html section | Live
9 | Nav → Solutions dropdown | Data Integration & Interoperability | solutions.html#data-integration | solutions.html section | Live
10 | Nav → Solutions dropdown | Master Data Management | solutions.html#mdm | solutions.html section | Live
11 | Nav → Solutions dropdown | Governance, Quality & Catalog | solutions.html#governance-quality-catalog | solutions.html section | Live
12 | Nav → Solutions dropdown | Analytics & Insights | solutions.html#analytics-insights | solutions.html section | Live
13 | Nav → Solutions dropdown | B2B & Data Exchange | solutions.html#b2b-data-exchange | solutions.html section | Live
14 | Nav → Solutions dropdown | Data Security & Privacy | solutions.html#data-security-privacy | solutions.html section | Live
15 | Nav → Solutions dropdown | DataOps & Observability | solutions.html#dataops-observability | solutions.html section | Live
16 | Nav → Solutions dropdown | AI & Agentic Solutions | solutions.html#ai-agentic-solutions | solutions.html section (+ link out to index.html#ai-automation) | Live
17 | Nav → Industries dropdown | 6 industries | industry-*.html | Dedicated industry page each | Live | All 6 confirmed present and linked.
18 | Nav → Partners | Partners (15 alliance/platform links) | #partners | Partners logo wall on index.html | Anchor-only | All 15 individual alliance/platform links point to the same generic anchor — no dedicated Partners page exists. See Missing / Planned Pages sheet.
19 | Nav → About dropdown | Who We Are / Careers / Contact Us | about.html / careers.html / contact.html | Dedicated pages | Live
20 | Nav → Resources dropdown | Blogs | #insights | Insights section on index.html | Anchor-only | That section actually shows 4 case-study teasers (tagged "CASE STUDY"), not blog content. No dedicated blog page exists. See Missing / Planned Pages sheet.
21 | Nav → Resources dropdown | Case Studies | case-studies.html | Dedicated page | Live
22 | Nav → Resources dropdown | FAQs | #faq | FAQ section on index.html | Anchor-only | By design — fine as a homepage section.
23 | Nav → Resources dropdown | Events | webinars.html | Dedicated page | Live
24 | Nav → Resources dropdown | Whitepapers | #insights | Insights section on index.html | Aliased | Aliased to the same anchor as Blogs, which shows case-study teasers — not whitepaper content. No dedicated page exists. See Missing / Planned Pages sheet.
25 | Nav → Resources dropdown | Newsroom | #insights | Insights section on index.html | Aliased | Aliased to the same anchor as Blogs, which shows case-study teasers — not press/news content. No dedicated page exists. See Missing / Planned Pages sheet.
26 | Footer → Services column | Advisory & Assessment | services.html#advisory-assessment | services.html, Advisory & Assessment section | Live | FIXED this cycle — was a dead href="#".
27 | Footer → Services column | Licensing & Reselling | services.html#licensing-reselling | services.html, Licensing & Reselling section | Live | FIXED this cycle — was a dead href="#".
28 | Footer → Services column | Training & Enablement | services.html#training-enablement | services.html, Training & Enablement section | Live | FIXED this cycle — was a dead href="#".
29 | Footer → Services column | Staff Augmentation | services.html#staff-augmentation | services.html, Staff Augmentation section | Live | FIXED this cycle — was a dead href="#".
30 | Footer → Services column | Implementation & Delivery | services.html#implementation-delivery | services.html, Implementation & Delivery section | Live | FIXED this cycle — was wrongly pointing to #partners (copy-paste bug).
31 | Footer → social icons | LinkedIn | [PLACEHOLDER: real aiDataWorks LinkedIn company URL] | Nowhere (placeholder) | Dead link | Literal placeholder text left in the href — needs the real company LinkedIn URL.

## Case Studies
Case Study Detail Pages (13)
Metadata pulled from the case-studies.html JSON data block that drives the live grid.
# | Slug | Industry | Service | File Path | site.js present?
1 | bfsi-microfinance-platform-modernization | BFSI — Microfinance | Master Data Management | case-studies/bfsi-microfinance-platform-modernization/index.html | Yes
2 | frost-bank-b2b-nacha-edi-modernization | Financial Services | B2B & Data Exchange | case-studies/frost-bank-b2b-nacha-edi-modernization/index.html | No
3 | life-sciences-mft-migration | Enterprise IT | B2B & Data Exchange | case-studies/life-sciences-mft-migration/index.html | No
4 | ai-data-quality-governance-idmc | Cross-Industry | AI & Agentic Solutions | case-studies/ai-data-quality-governance-idmc/index.html | No
5 | healthcare-ai-interoperability-patient-care | Healthcare | AI & Agentic Solutions | case-studies/healthcare-ai-interoperability-patient-care/index.html | Yes
6 | corewell-health-credentials-modernization | Healthcare | Legacy Modernization & Cloud Migration | case-studies/corewell-health-credentials-modernization/index.html | No
7 | retail-bde-cloud-migration | Retail & CPG | Cloud Data Platforms | case-studies/retail-bde-cloud-migration/index.html | No
8 | healthcare-sensitive-data-protection | Healthcare | Data Security & Privacy | case-studies/healthcare-sensitive-data-protection/index.html | No
9 | health-insurer-mainframe-governance | Insurance | Governance, Quality & Catalog | case-studies/health-insurer-mainframe-governance/index.html | No
10 | healthcare-managed-services-post-golive | Healthcare | Managed Services — DMaaS | case-studies/healthcare-managed-services-post-golive/index.html | No
11 | semiconductor-industry40-analytics-transition | Manufacturing | Analytics & Insights | case-studies/semiconductor-industry40-analytics-transition/index.html | No
12 | semiconductor-data-security-cloud-warehouse | Manufacturing | Data Security & Privacy | case-studies/semiconductor-data-security-cloud-warehouse/index.html | No
13 | healthcare-hl7-realtime-integration | Healthcare | Data Integration & Interoperability | case-studies/healthcare-hl7-realtime-integration/index.html | No

## Known Issues
Open Issues Found While Building This Tracker
Concrete, verifiable issues in the current codebase — not yet fixed. (3 prior items — dead footer links, the 6 stale legacy service pages, and index-v1.html — were resolved and removed from this list.)
# | Issue | Severity | Affected Pages | Recommendation
1 | 11 of 13 case-study detail pages (plus the build template) are missing the <script src="../../site.js"> tag, so the mobile hamburger menu / nav accordion JS never loads on those pages. | High | 11 case-study pages (see Page Inventory sheet, rows with 'BUG' note) + templates/case-study-template.html (low priority, not public) | Add the site.js script tag to each affected page, matching the two pages that already have it correctly (bfsi-microfinance-platform-modernization, healthcare-ai-interoperability-patient-care).
2 | Footer LinkedIn icon still contains literal placeholder text instead of a real URL: [PLACEHOLDER: real aiDataWorks LinkedIn company URL]. | Medium | index.html footer (site-wide via sync) | Swap in the real aiDataWorks LinkedIn company page URL.
3 | Whitepapers and Newsroom nav/footer entries both alias to the homepage #insights anchor, which now shows case-study teasers — not blog, whitepaper, or press content for any of the three nav items that point to it. | Medium | Nav Resources dropdown + footer, site-wide | See Page Inventory rows 32-34 (Blog, Whitepapers, Newsroom) — all three need real content from you before they can be built.